EUROPEAN DATA PROTECTION SUPERVISOR

Technology & Privacy Unit

PEDRRA

Pilot Test Protocol

Dry Run Plan • Observation Checklist • Hot Wash Debrief • Issue Framework

Version 1.0 — March 2026

# 1. Purpose & Objectives

The pilot test is a full dress rehearsal of the PEDRRA training with a small, representative group. Its purpose is to validate that all materials, activities, technology, and facilitation protocols work as intended before the full rollout.

## 1.1 Pilot Objectives

| # | Objective | Success Criterion |
| --- | --- | --- |
| PO1 | Validate scenario dynamics: use cases trigger intended debate, not immediate consensus | At least 2 out of 3 questions in each scenario produce split team opinions |
| PO2 | Calibrate timing: all activities fit within the 6-hour 15-minute window (including buffer) | No session runs more than 5 minutes over allocated time |
| PO3 | Test technology: EUDPR Training Platform handles simultaneous usage without failure | Quiz delivery and answer submission < 2 seconds; zero crashes during session |
| PO4 | Validate facilitator protocol: facilitators can manage debates and deadlocks | Facilitators resolve at least 1 deadlocked debate using inject cards or direct intervention |
| PO5 | Assess materials clarity: participants understand workbook instructions without facilitator explanation | No more than 2 clarification questions per scenario related to workbook instructions |
| PO6 | Test analog fallback: if the app fails, the analog kit can replace it seamlessly | Full switch to analog kit completed within 3 minutes (timed during pilot) |
| PO7 | Validate evaluation instruments: Level 1 survey and Level 2 quiz are clear and functional | Zero ambiguous questions identified; survey completion time < 10 minutes |

# 2. Participant Selection

## 2.1 Selection Criteria

The pilot group must be representative of the actual target audience. Recruit 6–8 participants meeting the following criteria:

| Criterion | Requirement | Rationale |
| --- | --- | --- |
| Group size | 6–8 participants (minimum 6) | Large enough for 2 teams of 3–4; small enough for detailed observation |
| Role diversity | Minimum: 1 IT/Security, 1 DPO, 1 LCO, 1 Legal/Management | Must replicate the inter-disciplinary dynamic of the actual training |
| EUIBA representation | At least 2 different EUIBAs | Tests inter-institutional perspective differences |
| EUDPR familiarity | Mix of experienced (3+ years) and newer (< 2 years) professionals | Tests whether the content level works for the expected range |
| Prior PEDRRA/PATRICIA participation | Maximum 2 participants from previous editions | Some continuity for comparison; majority fresh perspective |
| Technology comfort | Mix: at least 1 participant self-identified as “not comfortable” with apps | Tests whether the platform is intuitive for all users |
| Availability | Full day commitment (09:30–16:15) + 30 min Hot Wash debrief | Must complete the entire programme to validate timing |

## 2.2 Recruitment

- Coordinator (Laura) sends invitation 3 weeks before pilot date.

- Invitation explains: purpose of the pilot, expectations (participate fully + provide candid feedback), confidentiality (materials are pre-release), time commitment.

- Participants receive the pre-reading package 1 week before the pilot (same as actual training).

- Participants should NOT receive the solution keys or facilitator guide.

# 3. Pilot Day Plan

## 3.1 Schedule

The pilot follows the exact same schedule as the actual training, plus a 30-minute Hot Wash at the end.

| Time | Activity | Duration | Observer Focus |
| --- | --- | --- | --- |
| 09:00–09:30 | Pilot setup: materials, technology check, observer briefing | 30 min | Confirm all materials present; test app on venue Wi-Fi |
| 09:30–10:00 | Welcome & Context Setting | 30 min | Do participants understand the scenario context? Is the psychological safety briefing effective? |
| 10:00–10:45 | Scenario 1: The Encrypted Gateway | 45 min | Does the inject at T+15 shift debate? Are workbook instructions clear? |
| 10:45–11:00 | Plenary Discussion (Scenario 1) | 15 min | Does the plenary generate useful debate? Is the facilitator effective? |
| 11:00–11:15 | Coffee Break | 15 min | — |
| 11:15–12:15 | Lecture: Personal Data Breach Essentials | 60 min | Is the pace right? Are participants engaged throughout? |
| 12:15–13:15 | Lunch Break | 60 min | Informal feedback collection if possible |
| 13:15–14:00 | Scenario 2: The Inter-Agency Data Leak | 45 min | Does the health status indicator trigger debate? Is the inject effective? |
| 14:00–14:30 | Plenary Discussion (Scenario 2) | 30 min | Is 30 min enough for this complex scenario? |
| 14:30–15:00 | Practical Examples & Quiz [APP] | 30 min | Does the app work? Is the quiz engaging? Test analog fallback at 14:45. |
| 15:00–15:15 | Data Subject Communication Exercise | 15 min | Is 15 min enough? Do teams understand the Article 35 requirements? |
| 15:15–16:00 | Overall Debrief & Feedback | 45 min | Is the Knowledge Gaps exercise productive? Does the L1 survey work? |
| 16:00–16:15 | Buffer / Overrun | 15 min | Was the buffer needed? How much unused time? |
| 16:15–16:45 | HOT WASH DEBRIEF (pilot-specific) | 30 min | See Section 5 for debrief protocol |

## 3.2 Mandatory Technology Stress Test

During the Practical Examples session (14:30–15:00), the pilot must include a deliberate technology failure test:

Analog Fallback Test Protocol At 14:45 (15 minutes into the quiz session): the facilitator announces: “We have a technical issue with the app. Please put down your devices. We’re switching to the backup method.” The facilitator then: 1. Distributes the A/B/C/D cards and colour risk cards from the Analog Kit. 2. Reads the next quiz question aloud. 3. Teams hold up answer cards. Facilitator tallies on flip chart. Time this transition. Target: complete switch within 3 minutes. If it takes longer, the Analog Kit design needs revision. After 2 analog questions, the facilitator can “restore” the app if time permits.

# 4. Observation Checklist

Each observer completes this checklist during the pilot. Assign at least 2 observers (not facilitating).

| Observer Name |  |
| --- | --- |
| Date |  |
| Session Observed | [All / specific sessions] |

## 4.1 Materials & Instructions

Rate: ✓ (Good) / ~ (Adequate) / ✗ (Needs Revision)

| Item | Rating | Observation / Issue |
| --- | --- | --- |
| Participant Briefing (Part B) — clarity of scenario context |  |  |
| Participant Briefing — technical findings understandable to non-IT roles |  |  |
| Team Workbook (Part C) — questions clearly worded |  |  |
| Team Workbook — tables/templates easy to fill in |  |  |
| Risk Assessment Template — structure supports systematic analysis |  |  |
| Data Subject Communication template — clear what is expected |  |  |
| Inject Card — visually distinct, read-aloud format works |  |  |
| Pre-reading package — participants were prepared (observed in discussion quality) |  |  |
| Analog Kit — cards legible, right size, easy to hold up |  |  |

## 4.2 Scenario Dynamics

| Observation Point | Scenario 1 | Scenario 2 |
| --- | --- | --- |
| Did the scenario trigger genuine debate (split opinions)? |  |  |
| Did teams engage with all question blocks, or skip some? |  |  |
| Was the inject effective in shifting the assessment? |  |  |
| Did teams complete the risk assessment template? |  |  |
| Were there any confusing or ambiguous elements? |  |  |
| Did the 72-hour awareness trigger generate discussion? |  |  |
| Did the peer-review / plenary discussion add value? |  |  |
| How many clarification questions did teams ask? |  |  |
| Did any team reach the “correct” verdict for the wrong reasons? |  |  |

## 4.3 Timing

| Session | Allocated Time | Actual Time | Variance | Notes |
| --- | --- | --- | --- | --- |
| Welcome & Context Setting | 30 min |  |  |  |
| Scenario 1 team exercise | 45 min |  |  |  |
| Plenary Discussion (Sc. 1) | 15 min |  |  |  |
| Lecture | 60 min |  |  |  |
| Scenario 2 team exercise | 45 min |  |  |  |
| Plenary Discussion (Sc. 2) | 30 min |  |  |  |
| Practical Examples & Quiz | 30 min |  |  |  |
| Communication Exercise | 15 min |  |  |  |
| Overall Debrief & Feedback | 45 min |  |  |  |
| Buffer used? | 15 min |  |  |  |
| TOTAL | 6h 15m |  |  |  |

## 4.4 Technology

| Item | Pass/Fail | Notes |
| --- | --- | --- |
| App loads on all participant devices (phone, tablet, laptop) |  |  |
| Session code join works first time for all participants |  |  |
| Quiz questions display correctly (text, options, timer) |  |  |
| Answer submission < 2 seconds |  |  |
| Leaderboard displays correctly on projector |  |  |
| XP and badges trigger correctly |  |  |
| Level 1 survey works and submits anonymously |  |  |
| CSV export generates clean data |  |  |
| Wi-Fi sustained all devices simultaneously |  |  |
| Analog fallback switch completed within 3 minutes |  |  |

## 4.5 Facilitation

| Observation Point | Rating (✓/~/✗) | Notes |
| --- | --- | --- |
| Facilitator delivered instructions clearly |  |  |
| Facilitator managed time effectively |  |  |
| Facilitator handled the “Risk vs. High Risk” debate well |  |  |
| Facilitator used the inject card effectively |  |  |
| Facilitator resolved at least one deadlocked debate |  |  |
| Facilitator created a psychologically safe environment |  |  |
| Facilitator adapted to unexpected situations |  |  |
| Facilitator engaged quieter participants |  |  |
| Transitions between sessions were smooth |  |  |
| Facilitator used the Watch Points from the guide effectively |  |  |

## 4.6 Participant Engagement

| Observation Point | Rating (✓/~/✗) | Notes |
| --- | --- | --- |
| Participants were engaged during the lecture |  |  |
| All team members contributed to discussions |  |  |
| Hierarchy bias was observed (junior staff silent) |  |  |
| Participants used the app without difficulty |  |  |
| Participants found the gamification motivating |  |  |
| Participants engaged with the data subject communication exercise |  |  |
| Participants completed the knowledge gaps exercise seriously |  |  |

## 4.7 Enhancement Materials

Observe how the new enhancement materials perform during the pilot.

Risk Assessment Primer: Did participants read it during Welcome? Did it help them start Scenario 1 more confidently? Did it reduce the number of “I don’t know where to start” moments?    Rating: ✓ / ~ / ✗

Team Role Cards: Did participants adopt their assigned roles? Did role assignment improve discussion quality? Did it prevent one person from dominating? Were roles rotated for Scenario 2?    Rating: ✓ / ~ / ✗

Pre-Filled Communication Template: Did the scaffolding help teams focus on the hard parts (consequences, self-protection)? Was 15 minutes sufficient with the template? Was the pre-filled content accurate and useful?    Rating: ✓ / ~ / ✗

Scoring Rubrics: Were facilitators able to complete the rubrics post-session? Were the criteria clear and the 3-point scale sufficient? Did the rubrics take a reasonable time to complete (target: 10 minutes per team per scenario)?    Rating: ✓ / ~ / ✗

Pre-Reading Package: Were participants prepared? Did the 10-page limit work (participants actually read it)? Were any sections unnecessary or missing?    Rating: ✓ / ~ / ✗

# 5. Hot Wash Debrief Protocol

The Hot Wash is a structured debrief held immediately after the pilot (16:15–16:45). It captures qualitative feedback while the experience is fresh.

## 5.1 Ground Rules

- Candour is essential — we need honest feedback, not politeness.

- Everything said is for improvement purposes only — no attribution in the report.

- Focus on what can be fixed, not what went perfectly.

- Every participant speaks at least once.

## 5.2 Structured Questions

The facilitator leads the debrief using these questions. Allow 3–4 minutes per question.

### Round 1: Overall Impression (5 min)

Q1: In one word, describe your overall experience of the training today.

Go around the table. Note the words. This gives an immediate temperature check.

### Round 2: Materials & Clarity (5 min)

Q2: Was there any point where you were confused by the instructions, the workbook, or the scenario materials? Be specific.

Q3: Was the pre-reading package useful? Did it prepare you adequately?

### Round 2b: Enhancement Materials (3 min)

Q3b: Did the Risk Assessment Primer help you get started with Scenario 1, or was it unnecessary?

Q3c: Did the Team Role Cards affect how your team worked together? Positively or negatively?

Q3d: Was the pre-filled Communication Template helpful, or would you have preferred a blank slate?

### Round 3: Scenarios & Activities (8 min)

Q4: Did Scenario 1 (Stolen Laptop) feel realistic? Was it too easy, too hard, or about right?

Q5: Did Scenario 2 (Cloud Leak) force a genuine “Risk vs. High Risk” debate in your team? What was the hardest part?

Q6: Was the data subject communication exercise (15 min) useful? Was 15 minutes enough?

Q7: Did the inject cards change your team’s assessment? Did you feel the timing was right?

### Round 4: Technology & Logistics (5 min)

Q8: How was the app experience? Easy to use? Any glitches?

Q9: Did the gamification (XP, badges, leaderboard) add to the experience or distract from it?

Q10: Were there any logistics issues (room, materials, timing, breaks)?

### Round 5: Facilitation (4 min)

Q11: Did you feel comfortable speaking up, even if your view differed from senior colleagues?

Q12: Was the facilitator’s guidance helpful without being directive?

### Round 6: Final (3 min)

Q13: If you could change one thing about this training, what would it be?

Q14: Would you recommend this training to colleagues at your EUIBA?

# 6. Issue Categorisation Framework

After the pilot, compile all findings from the observation checklists and the Hot Wash. Categorise each issue using this framework.

## 6.1 Severity Categories

| Category | Definition | Action Required | Timeline |
| --- | --- | --- | --- |
| MUST-FIX | Blocks a learning objective, causes confusion, or creates a factual error. The training cannot proceed without fixing this. | Must be resolved before Go/No-Go decision. | Within 2 weeks of pilot |
| SHOULD-FIX | Degrades the experience or reduces effectiveness, but does not block learning objectives. | Should be resolved before delivery if feasible. If not, document as a known limitation. | Within 2 weeks of pilot (best effort) |
| NICE-TO-HAVE | Minor improvement that would enhance the experience but has no impact on learning outcomes. | Document for next edition. Do not delay delivery. | PEDRRA II backlog |

## 6.2 Issue Categories

| Category | Examples |
| --- | --- |
| Content | Factual error in a scenario; ambiguous quiz question; missing EUDPR reference; unrealistic technical detail |
| Design | Timing too tight for a block; activity sequence doesn’t build logically; an objective is not adequately assessed |
| Materials | Workbook instruction unclear; template too small to write in; inject card not visually distinct enough |
| Technology | App crashed; quiz didn’t load; leaderboard displayed incorrectly; analog fallback switch too slow |
| Facilitation | Facilitator missed a Watch Point; debate wasn’t managed well; transition was confusing |
| Logistics | Room too small; A/V didn’t work; materials arrived late; catering issue |

## 6.3 Issue Log Template

Use this template to log all issues identified during the pilot.

| # | Issue Description | Category | Severity | Source | Owner | Resolution | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |

# 7. Go / No-Go Decision Framework

After all MUST-FIX issues are resolved, the project lead presents the pilot findings to the approvers for a Go/No-Go decision.

## 7.1 Go/No-Go Criteria

| Criterion | Threshold for GO | Status |
| --- | --- | --- |
| All MUST-FIX issues resolved | 100% resolved | ☐ |
| SHOULD-FIX issues resolved or documented | 80% resolved or documented as known limitations | ☐ |
| Technology stress test passed | App handles full load; analog fallback tested successfully | ☐ |
| Timing validated | All sessions within +5 min of allocation | ☐ |
| Facilitator protocol validated | Facilitators can manage debates and deadlocks effectively | ☐ |
| Evaluation instruments validated | L1 survey and L2 quiz functional; no ambiguous questions | ☐ |
| Materials finalised | All workbooks, inject cards, analog kits print-ready | ☐ |

## 7.2 Decision Record

| Decision Date | [Date] |
| --- | --- |
| Decision | [GO / NO-GO / GO WITH CONDITIONS] |
| Conditions (if applicable) | [List any conditions that must be met before delivery] |
| Approved By | [Name, Title] |
| Approved By | [Name, Title] |

If NO-GO If the decision is NO-GO, document the specific blockers and the plan to resolve them. Schedule a mini-pilot (2–3 hours, focused on the blocked areas) after fixes are implemented. The mini-pilot does not require the full protocol — focus only on the areas that caused the NO-GO.

# 8. Pilot Report Summary

Complete this summary after the pilot and before the Go/No-Go meeting.

| Pilot Date | [Date] |
| --- | --- |
| Participants | [Number] participants from [Number] EUIBAs |
| Facilitators | [Names] |
| Observers | [Names] |
| Venue | [Location] |

## 8.1 Pilot Objectives Achievement

| Objective | Met? | Evidence |
| --- | --- | --- |
| PO1: Scenario dynamics trigger debate |  |  |
| PO2: Timing fits within 6h 15m |  |  |
| PO3: Technology handles load |  |  |
| PO4: Facilitator protocol works |  |  |
| PO5: Materials clarity |  |  |
| PO6: Analog fallback works |  |  |
| PO7: Evaluation instruments clear |  |  |

## 8.2 Issue Summary

| Severity | Count | Resolved | Pending |
| --- | --- | --- | --- |
| MUST-FIX |  |  |  |
| SHOULD-FIX |  |  |  |
| NICE-TO-HAVE |  |  |  |
| TOTAL |  |  |  |

## 8.3 Key Findings

What worked well:

What needs to change before delivery:

What should be changed for PEDRRA II (not blocking delivery):

## 8.4 Recommendation

[GO / NO-GO / GO WITH CONDITIONS — with rationale]