10 September 2025

|

v.0.1 | September 2025

“PEDRRA”

PErsonal Data bReach Risk Assessment

Instructional Design Blueprint (A.D.D.I.E Model)

EDPS European Data Protection Supervisor

Version History

| Version 0.1 | 10 September 2025 | First Draft of the document. |
| --- | --- | --- |
| Version 0.2 | 6 February 2026 | Second draft. Established the Learning objectives. |

Table of contents

1. Introduction: A systematic Approach to Training Design	3

2. Phase 1: Analyse	4

2.1.	Problem Identification & Training Needs Analysis (TNA)	4

2.2.	Target Audience Analysis	4

2.3.	Training Goal	5

2.4.	Resource & Risk Analysis	5

3. Phase 2: Design	8

3.1.	Learning Objectives (SMART & Bloom´s Taxonomy.	8

3.2.	Instructional Strategy	9

3.3.	Course Structure & Sequencing	10

3.4.	Assessment & Evaluation Methods	10

4. Phase 3: Develop	12

4.1.	Training Materials Development	12

4.2.	Activity Development	12

4.3.	Quality Assurance (QA) & Piloting	13

4.3.1. Subject Matter Expert (SME) Review	13

4.3.2. Technology Stress Test	13

4.3.3. The Pilot Test (Dry Run)	13

4.3.4. Iterative Refinement	14

5. Phase 4: Implement	15

5.1.	Rollout Plan	15

5.2.	Facilitators' Responsibilities	15

5.3.	Technology Used	16

5.4.	Delivery Logistics	16

6. Phase 5: Evaluate	17

6.1.	Feedback Collection Methods	17

6.2.	Evaluation Metrics	17

6.3.	Improvement Strategy	17

# Introduction: A systematic Approach to Training Design

This document outlines the comprehensive instructional design blueprint for the PEDRRA training activity, structured according to the A.D.D.I.E. model. This framework—encompassing Analyze, Design, Develop, Implement, and Evaluate—is the established standard for effective training development and provides a systematic, evidence-based approach to creating learning experiences that are purposeful and strategically aligned with organizational needs. This introduction explains how each phase of the A.D.D.I.E. model was specifically applied to shape the PEDRRA training activity, the details of which are elaborated in the subsequent sections of this blueprint.

The Analyze phase feeds from the weaknesses identified through the Data Breach Notifications Management activity led by the TP SOTA Unit and from the feedback obtained during the 2024 Data Breach Management Awareness project. Critical performance gaps in the controller’s ability to deliver clearly the rationale behind its risk assessment output(s) are identified. Additionally, with the rising use of AI, it is observed that risk assessment is apprehended with some (unexpected) questioning and challenges by the controllers.

In the Design phase, the above findings were translated into a strategic blueprint for the exercise. This involved crafting five SMART (Specific, Measurable, Achievable, Relevant, Time-bound) learning objectives that directly address the gaps identified during the analysis.  “An interactive and collaborative in-person classroom” format was selected to align with adult learning principles, promoting problem-centered and collaborative learning for the target audience of EUIBA professionals, along with a data breach risk assessment lecture.

The Develop phase focused on creating all the tangible instructional materials required for the exercise. This included writing different use cases serving as practical exercises to resolve collaboratively and as group works to be presented in front of the class. Key resources will also be developed, such as interactive interface to leverage participants’ engagement, comprehensive pre-and post-reading materials, solution factsheets and questionnaires to guide team discussions.

The Implement plan details how the training will be delivered. It outlines an in-person “class-room” format for participants from EUIBAs. The plan includes facilitated plenary discussions, expert guidance from EDPS facilitators to clarify complex points and ensure learning objectives are met, and work group use case evaluations.

Finally, the Evaluate phase is designed to measure the exercise's effectiveness and envisage future improvements. This will be accomplished through the collection of anonymous participant feedback and the drafting of a comprehensive After Action Report (AAR). This report will analyze the exercise's outcomes against its objectives and provide actionable recommendations, ensuring the A.D.D.I.E. cycle continues by feeding directly into the analysis phase for the next iteration of the PEDRRA series.

# Phase 1: Analyse

The Analyse phase serves as the foundation for the entire training lifecycle, as emphasized in the EDPS Guide to Effective Training. Its purpose is to ensure that the training is a necessary, relevant, and precisely targeted solution to a clearly identified problem.

## Problem Identification & Training Needs Analysis (TNA)

Stemming from the analysis of the notification contents, case closure recommendations and feedback from the 2024 Awareness Program, the following identified gaps constitute the core problem that PEDRRA is designed to address:

- Finding #1: Low maturity in performing data breach risk analysis - Based on the submitted notifications collected by the TP Data Breach Team, the quality of the risk assessment regularly does not meet the expected standards. Alongside not adequately defining the surface of attack (e.g., data category, data subjects’ profiles), the risk assessment rationale is not clearly laid down with properly identified adverse effects and associated increasing/decreasing factors leading to properly score the risk. In absence of such clear demonstration, the controller may certainly not meet the principle of accountability.

- Finding #2: A data breach risk assessment centered on the organization - The controllers do not properly put at the center the data subjects of the assessment. Organizational risks permeate the data breach risk assessment. Such approach may lead to avoid apprehending correctly and honestly the risk score for the data subjects.

Finding #3: A high tolerance to risk - In the context of data breach risk assessment, the controller usually leans towards under-evaluating the risk level as to avoid communicating about the breach to the affected data subjects and even the authority. Controllers even develop a risk matrix where high-risk is split in two paths of decision (notify/not notify) contradicting the 3-tier risk level as described in the law.

Finding #4: Inadequate Management of Data Subject Communications – When a breach is identified as "High Risk," controllers frequently struggle to elaborate a proper communication to the affected individuals. The communication often lacks the necessary components required by Article 35, such as a clear description of the nature of the breach, the likely consequences for the data subject, and the specific mitigation measures the individual should take. There is a noticeable tendency to use overly technical or vague language, which fails to empower the data subject to protect themselves, thereby undermining the controller's accountability.

## Target Audience Analysis

The training is designed for professionals from EUIBAs who are directly involved in incident response and data protection. This audience is characterized by a preference for problem-centered, experience-based learning.

- Primary Roles:

  - Legal Teams & Senior Management: Personnel involved in strategic decision-making, risk management, and legal compliance.

  - Operational Managers: Managers who are responsible for the security of the assets where personal data are processed.

  - IT Security Personnel and data owners: Technical staff from NOC/SOC/ICT departments who are the first responders to cybersecurity incidents including Local Information Security Officers (LISO) and Local Cybersecurity Officers (LCO) responsible for security incident procedures and compliance with the Cybersecurity Regulation.

  - Data Protection Officers (DPOs: Staff responsible for advising on and monitoring compliance with Regulation (EU) 2018/1725 (EUDPR).

  - Business Continuity/Crisis Management Teams: Roles responsible for organizational resilience and response to major disruptions.

  - Risk officers: Risk officers analyze, measure, and mitigate potential threats—operational, financial, or strategic—that could damage an organization's assets, earnings, or reputation. They establish risk frameworks, monitor compliance, and advise leadership to ensure business continuity and regulatory adherence.

## Training Goal

The overall goal of the PEDDRA exercise is to raise the capabilities of EUIs to operate a mature personal data breach risk assessment and manage the associated decision-making process expected outcomes in line with Article 34 and 35 of the Regulation.

## Resource & Risk Analysis

Financial Resources

TBD

Human Resources

T&P: Laura, Jose, Dina, and Kris.

I&C: TBD

Risk Management Table

This table identifies potential risks to the successful delivery of the PEDRRA training and outlines mitigation strategies to ensure learning objectives are met regardless of disruptions.

| Risk Category | Potential Risk | Impact (High/Med/Low) | Mitigation Strategy & Contingency Plan |
| --- | --- | --- | --- |
| Technology | Failure of the Gamification/Training App or venue Wi-Fi connectivity. | High | Mitigation: Test Wi-Fi load capacity during the Pilot phase, and before the training activity. Contingency: Have printed "Analog Kits" (paper questionnaires and large-format risk matrices) ready for every table to switch modes instantly. |
| Pedagogical | "Analysis Paralysis": Teams get stuck debating the proposed use cases within the established work groups or during peer-review sessions. | High | Mitigation: Train facilitators to recognize circular debates. Contingency: Facilitators are authorized to use a "Inject Card" that forces a discussion (e.g., "New Intel: The data has appeared on the Dark Web"), compelling the team to treat it as High Risk move on. |
| Engagement | Hierarchy Bias: Junior staff (e.g., LCOs) hesitate to speak up or correct Senior Management/DPOs during the simulation. | Medium | Mitigation: Establish "Psychological Safety" rules (Chatham House Rule) during the intro. Contingency: Facilitators actively solicit input from quieter roles using direct questions (e.g., "From a technical standpoint, does the LCO agree with this assessment?"). |
| Content | Use Case and Quiz Credibility: participants quality (lawyers vs AI coordinator vs LSO) challenge the plausibility of the specific use cases solutions and examples described. | Medium | Mitigation: Conduct a rigorous Subject Matter Experts Review (IT Security & Legal) of all technical elements during the Development Phase. Contingency: Facilitators act as the "Game Master" to overrule technical disputes: "For the purpose of this exercise, assume the exploit was successful as described." |
| Logistics | Time Management: ensure to deliver all the parts in the established time allocation, in particular with the work group presentation session with at least 2 work groups’ work. | High | Mitigation: Rehearse the lecture timing strictly. Contingency: If the work group presentations are too long, reduce to one and the rest of the group works are reviewed and corrected post-class by the team in charge of the exercise. |

# Phase 2: Design

The Design phase acts as the architectural stage of the A.D.D.I.E. model, transforming the "what" and "why" identified during the Analyse phase into a strategic "how." As outlined in the EDPS Guide to Effective Training, this involves creating a detailed blueprint that guides all subsequent development. For PEDRRA, this meant translating the specific findings into measurable SMART learning objectives. The instructional strategy—class-room format with practical exercise—was deliberately chosen to align with adult learning principles suitable for the experienced, multi-disciplinary EUIBA’s professionals being trained. The course structure and content sequencing were meticulously planned to create a logical learning progression that directly addresses participant feedback from the previous exercise.

## Learning Objectives (SMART & Bloom´s Taxonomy.

The following SMART (Specific, Measurable, Achievable, Relevant, Time-bound) objectives have been designed to address the identified needs:

- Differentiate Organizational Risk from Data Subject Risk [Understanding / Analysis]: By the end of the "Personal Data Breach Essentials" lecture, participants will be able to distinguish between organizational impacts and adverse effects on data subjects, correctly identifying at least three specific data subject risks (e.g., identity theft, loss of control) that must be prioritized in an EUDPR-compliant assessment.

- SMART Alignment: Addresses Finding #2 (organization-centered risk) by refocusing the assessment lens.

- Apply EDPS Methodology [Apply / Analyse]: Following the "Personal Data Breach Essentials" lecture, participants will apply the EDPS-standard risk assessment methodology to three distinct data breach use cases, identifying at least 80% of the key risks to data subjects and integrating these findings into a standardized risk assessment template.

- SMART Alignment: Directly addresses Finding #1 (low maturity in methodology) and Finding #2 (neglecting data subject impact) by requiring a high degree of accuracy in risk identification.

- Formulate a Risk Assessment Rationale [Create/Evaluate]: During the "Use Case Exercise," participants will construct a written rationale for a risk score (Low, Medium, High) that explicitly maps the "surface of attack" to specific increasing or decreasing risk factors as defined in EDPS guidelines.

- SMART Alignment: Addresses Finding #1 regarding the inability to deliver clearly the rationale behind risk assessment output.

- Determine Notification Obligations [Evaluate]: Given a complex data breach use case, participants will decide whether a breach requires notification to the EDPS and/or communication to data subjects within the legal 72-hour framework, justifying the decision based on the 3-tier risk level described in the law.

- SMART Alignment: Addresses Finding #3 (high risk tolerance and incorrect decision paths).

- Critically Review Peer Risk Assessments [Evaluate]: During the "Peer-Review" session, participants will critique the risk assessment output of another group, identifying at least one potential under-evaluation of risk or one missing data subject profile using the provided rubric.

- SMART Alignment: Addresses Finding #3. Encourages collaborative learning and corrects the "under-evaluation" bias identified in the analysis.

- Manage Data Subject Communication [Create/Evaluate]: For breaches identified as high-risk, participants will draft a formal notification to data subjects that includes all mandatory Article 35 elements—the nature of the breach, likely consequences, and mitigation steps—using clear, non-technical language.

- SMART Alignment: Addresses Finding #4. Corrects the difficulty controllers face in elaborating proper, transparent communications that empower data subjects..

## Instructional Strategy

PEDRRA will employ a multi-faceted instructional strategy, combining several methods to create a comprehensive and engaging learning experience. This blended approach is designed to cater to diverse learning preferences and address the specific needs as identified through.

The core of the training is a “in-person classroom geared towards learning by examples” framed with active interaction, problem-centered, and collaborative learning—key tenets of adult learning theory. The format requires participants to apply their knowledge to realistic situations based on individual and collaborative participation.

This experiential learning is strategically supplemented by other instructional methods:

- Direct Instruction: A formal lecture on "Personal Data Breach Essentials" and “Risk Assessment Framework” will be delivered to provide foundational knowledge and learn by experience (CEPOL Testimony).

- Collaborative Learning: Facilitated plenary discussions after each example and a comprehensive debriefing session at the end of the day will allow participants to share their approaches, learn from diverse perspectives, and collectively construct a deeper understanding of best practices.

- Case-Based Learning: A dedicated session for the realization of the mandatory group works stemming from the provided use cases will be included to connect theoretical concepts to real-world application.

- Expert Guidance: Throughout the exercise, EDPS facilitators will provide continuous expert guidance and coaching, clarifying complex points and reinforcing best practices in real-time.

- Technology-Enhanced Learning: To complement the use case-based discussions, the training will utilize a custom web-based application, the "EUDPR Training Platform," to drive engagement and provide immediate performance data. This tool employs gamification elements (XP, badges) to foster friendly competition and utilizes instant feedback loops to reinforce learning objectives in real-time.

This combination of strategies ensures that participants not only engage in hands-on problem-solving but also receive the necessary theoretical grounding and expert reinforcement to build lasting capabilities.

## Course Structure & Sequencing

The 6-hour training is structured to build knowledge and skills, following a detailed agenda:

- Welcome and Introduction: Sets the context.

- Lecture: "Personal Data Breach Essentials: EDPS Perspective, Risk Assessment, and Notification" (New data DB risk assessment tool): This lecture, directly addresses participants' requests for "more explicit guidance from the EDPS" and an "introduction to the topic 'Data Breaches' from the perspective of the EDPS". It provides the foundational knowledge needed for the more complex subsequent use cases. CEPOL will present their experience following the 2024 data breach.

- Interactive quiz - During this section, the participants will be asked to participate in a quiz. The examples will be the object of further debrief.

- Intermediary wrap-up - This section will include plenary discussion about the information and explanations provided.

- Use case exercise - Hands-on practice on a given use case. Participants will be demanded to produce a risk assessment on the provided data breach use case (Review of real-world case studies from EDPS guidelines to solidify understanding of risk levels and notification decisions.)

Peer-Review - The participants collectively will review the work of 2 groups. The other work group risk assessment will be corrected post-training.

- Overall Training Debrief and Feedback: A final session for reflection, feedback collection, and discussion of future training needs and improvements.

## Assessment & Evaluation Methods

The evaluation will be multi-faceted, incorporating Kirkpatrick's Four-Level Model to measure effectiveness comprehensively:

- Level 1 (Reaction): An anonymous feedback form will be used to gather participant satisfaction with the content, facilitation, and overall experience.

- Level 2 (Learning): Team responses to the use cases questionnaires will be analyzed to assess the acquisition of knowledge and the ability to apply risk assessment and coordination principles.

- Level 3 (Behavior): The EDPS will usethe post-exercise After Action Report (AAR) to assess this level, which will provide actionable recommendations designed to influence and improve actual work practices and internal processes within EUIBAs.

- Level 4 (Results): The long-term impact will be measured by the adoption of the AAR recommendations and a potential reduction in compliance issues or improved breach notifications from participating EUIBAs in the future.

# Phase 3: Develop

The Develop phase is the production stage of the A.D.D.I.E. model, where the design blueprint is brought to life through the creation of all learning materials and resources. This phase moves from planning to creation, ensuring that every element is crafted to be accurate, engaging, and effective. For PEDRRA, this involved more than just preparing presentations; it meant developing complex, realistic examples and specific pedagogical tools, such as mock-up RoPAS or risk assessment templates, to create a more challenging and practical learning experience. Every resource, from pre-reading packages to facilitator guides, is developed in this phase to support the learning objectives and instructional strategy.

## Training Materials Development

The following materials will be created and compiled:

- Use Case Descriptions.

- Participant Workbooks: Including questionnaires for the use cases, mock-up RoPA, mock-up DPIA.

- Facilitator's Guide: A comprehensive guide for facilitators with presentation slides, use cases, timing cues, key discussion prompts, and expected learning outcomes.

- Pre-reading Package: A curated set of documents for participants to review beforehand, including:

  - Excerpts from Regulation (EU) 2018/1725 (EUDPR) and Regulation (EU, Euratom) 2023/2841 (Cybersecurity Regulation).

  - Relevant EDPS and EDPB guidelines on personal data breach notification.

  - Role-specific information sheets to simulate realistic information silos and compel collaboration.

- Practical Tools:

  - Risk assessment templates, for personal data breach accessible from the online platform used during the seminar.

  - Real-case examples from EDPS guidelines for analysis.

  - A base glossary for the terminology alignment activity.

- Evaluation Instruments: An anonymous feedback form for post-exercise data collection, along with rubrics for evaluating the quality of the developed glossaries, process maps, and communication protocols.

## Activity Development

The core learning activities will be developed to be highly interactive and collaborative:

- Examples-Solving: For each example, participants will be requested to provide an answer, possibly debate about it.

- Facilitated Plenary Discussions: Following each team session, a facilitator will lead a group discussion, inviting teams to share their findings and debating different approaches to foster peer-to-peer learning.

- Collaborative Development Sessions: Dedicated time for teams to work on the use case to put into practice what they learned during the morning sessions.

- Final Debriefing Session: An open forum for participants to reflect on key takeaways, discuss challenges in inter-role collaboration, and provide suggestions for future training.

## Quality Assurance (QA) & Piloting

To ensure the training is factually accurate, technically viable, and pedagogically effective, a rigorous Quality Assurance (QA) process will be implemented prior to the full rollout.

### Subject Matter Expert (SME) Review

Before the materials are finalized, a targeted review will be conducted to validate the realism and legal accuracy of the content.

- Legal Validation: A senior Legal Officer will review the "Solution Keys" for the second use case ("The Inter-Agency Data Leak") to ensure the interpretation of "High Risk" regarding the health status indicators aligns strictly with EDPS guidelines and current case law.

- Technical Validation: An IT Security expert will review the technical details of the use cases and examples used in the training and for the work groups.

### Technology Stress Test

Given the reliance on the "EUDPR Training Platform" for engagement, a specific technical QA phase is required.

- Functionality Check: The development team will verify that the gamification logic (awarding XP and Badges) triggers correctly upon answer submission and that the "Leaderboard" visualizes correctly on the main presentation screen.

- Load Testing: A connectivity test will be performed at the physical venue to ensure the Wi-Fi bandwidth can support simultaneous app usage by all participants without latency.

### The Pilot Test (Dry Run)

A full "dress rehearsal" will be conducted with a small, representative group (6-8 participants) comprising at least one IT staff member, one DPO, and one LCO. The pilot will focus on:

- Use Case and Quiz Dynamics: validating that the use cases designed successfully triggers the intended debate between participants, rather than immediate consensus.

- Timing Calibration: Confirming that the different designed activities can be realistically completed within the allocated 6-hour window.

- Facilitator Protocol: Testing the effectiveness of the facilitators soft skills, training capabilities and mechanism to resolve deadlocked debates.

### Iterative Refinement

Following the pilot, a "Hot Wash" debrief will be held to gather qualitative feedback. Any friction points—such as confusing wording in the app questions or unrealistic timing in the lecture—will be corrected in the materials before the final "Go/No-Go" decision for implementation.

# Phase 4: Implement

The Implement phase is the "live" execution stage of the A.D.D.I.E. model, where the meticulously planned and developed training is delivered to participants. As emphasized in the EDPS Guide to Effective Training, successful implementation requires careful management of the learning environment and the crucial role of the facilitator. For PEDRRA, this is not a passive presentation but a dynamic, facilitated exercise. The in-person, team-based format is designed to simulate real-world collaboration within EUIBAs. A critical component of implementation is the creation of a psychologically safe environment, a key tenet of adult learning, to encourage open and honest discussion about procedural weaknesses without fear of judgment.

## Rollout Plan

- Format: A 6-hour, in-person training event conducted in a single day.

- Environment: A venue conducive to both small team breakout work and larger plenary discussions.

- Schedule: The training will follow the detailed session breakdown outlined in the Design phase.

- Participant Onboarding: Pre-reading materials and logistical information will be distributed to registered participants in advance to ensure they arrive prepared.

## Facilitators' Responsibilities

EDPS facilitators will be central to the exercise's success. Their responsibilities include:

- Delivering the introduction and presenting the use cases clearly.

- Guiding teams during breakout sessions, answering clarifying questions, and ensuring they remain on task.

- Leading the plenary discussions, encouraging participation from all roles, and highlighting key learning points.

- Providing expert guidance on EDPS's perspective, particularly regarding risk assessment methodologies and notification obligations.

- Managing time effectively to ensure the agenda is followed.

- Facilitating the final debriefing session and encouraging candid feedback.

- Undergoing specific training on the new collaborative activities and how to facilitate them effectively.

- Creating a “Safe Space”

  - Chatham House Rule: Explicitly state that the session operates under non-attribution rules to encourage honest discussion about internal process failures.

  - "No Blame" Policy: Instruct facilitators to frame incorrect answers as "learning opportunities" rather than compliance failures.

## Technology Used

- Presentation Software: For delivering use case information and lecture content.

- Online Survey Tools: For the efficient and anonymous collection of participant feedback at the conclusion of the exercise.

- Collaborative Digital Tools: For real-time development of glossaries, process maps, and communication protocols (e.g., shared documents, digital whiteboards).

## Delivery Logistics

- Venue: A physical location will be secured that can accommodate the required number of participants and allows for both plenary sessions and separate tables for team-based work.

- Team Composition: Participants will be grouped by their EUIBA of origin to simulate real-world internal collaboration dynamics.

- Materials: All necessary materials (workbooks, pens, pre-reading printouts) will be provided to participants on-site.

# Phase 5: Evaluate

The Evaluate phase is the final and cyclical component of the A.D.D.I.E. model, crucial for measuring impact and driving continuous improvement, as highlighted in the EDPS Guide to Effective Training. For PEDRRA, evaluation extends far beyond simple satisfaction surveys. It employs the multi-level Kirkpatrick Model to systematically measure outcomes, from immediate participant reactions (Level 1) and knowledge acquisition (Level 2) to tangible changes in workplace behaviour (Level 3) and organizational resilience (Level 4). The key output, the After Action Report, is designed not merely to document the event but to provide actionable recommendations for EUIBAs and to serve as the foundational analysis for the next iteration of the PEDRRA series, thus completing and restarting the A.D.D.I.E. cycle.

## Feedback Collection Methods

- Immediate Feedback: An anonymous feedback form will be administered at the end of the session to capture Level 1 (Reaction) data on content relevance, facilitation quality, and overall satisfaction.

- Learning Assessment: The completed questionnaires from the use case sessions will be collected and analysed to measure Level 2 (Learning) outcomes, assessing the quality of risk assessments and the coherence of response plans.

- Behavioral Change Assessment: A follow-up survey will be sent to participants and their managers three months after the training to assess the application of learned skills and the implementation of developed resources (Level 3).

## Evaluation Metrics

- Participant Satisfaction: Quantitative ratings and qualitative comments from the feedback forms.

- Knowledge & Skill Application: Quality and completeness of team responses, demonstrating understanding of risk assessment, notification timelines, and inter-role coordination.

- Identified Process Gaps: Analysis of participant discussions and AAR feedback to identify common challenges and areas for improvement within EUIBA processes.

- Behavioural Change: Self-reported changes in on-the-job behaviour and collaboration patterns from the follow-up survey.

- Organizational Impact: Long-term metrics such as a reduction in the time to notify the EDPS of a breach, an increase in the quality of notifications, and a decrease in reported inter-departmental friction during incident response (Level 4).

## Improvement Strategy

The evaluation culminates in the creation of a comprehensive After Action Report (AAR).

- Analysis: The AAR will synthesize all collected data, including team responses and feedback, to identify key findings, successes, and areas for improvement.

- Recommendations: The report will provide concrete, actionable recommendations for participating EUIBAs to enhance their internal processes, communication protocols, and staff training (Level 3 - Behavior).

- Continuous Improvement Cycle: The findings and recommendations from the PEDRRA AAR will serve as the primary input for the Analyze phase of the next iteration of the PEDRRA II exercise, ensuring the program evolves to meet the changing needs of the EUIBAs and the evolving threat landscape.

Raising Awareness about Personal Data Breach Management - https://20years.edps.europa.eu/en/initiatives/raising-awareness-personal-data-breaches.html

“Risk assessment chilling effect” - the controllers do not know where to start as they are faced with a lot of unknowns.

The on-line class format is also a possible format. However, it is preferrable to run such format in future PEDRRA trainings after acquiring a first hand-on experience with the proposed PEDRRA I exercice.

The teams are established by the classroom  trainers.